## Timeline
HSS Block | Activity | YEAR 1 |  |  |  | YEAR 2 |  |  |  | YEAR 3
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Governance and Leadership | Form multisectoral steering committee and hold regular meetings
Advocate for DR inclusion in national health policy | bar: YEAR 1 Q2 to YEAR 1 Q4
Develop comprehensive DR program guidelines | bar: YEAR 1 Q2 to YEAR 2 Q1
Health Financing | Lobby for DR budget allocations at national level | bar: YEAR 1 Q2 to YEAR 3 Q1
Establish partnerships with private sector | bar: YEAR 1 Q3 to YEAR 2 Q2
Health Workforce | Create DR screening and referral training modules | bar: YEAR 1 Q2 to YEAR 1 Q3
Train CHWs and others in early detection, referral and treatment of DR | bar: YEAR 1 Q4 to YEAR 2 Q3
Health Information Systems | Set up DR data collection and reporting systems | bar: YEAR 1 Q3 to YEAR 2 Q2
Incorporate DR metrics into national health records | bar: YEAR 2 Q1 to YEAR 2 Q4
Collect data on DR indicators | bar: YEAR 2 Q3 to YEAR 3 Q2
Service Delivery | Establish DR screening units at NCD clinics | bar: YEAR 1 Q4 to YEAR 2 Q3
Establish referral systems | bar: YEAR 1 Q4 to YEAR 2 Q3
Perform DR screening in clinics | bar: YEAR 2 Q2 to YEAR 3 Q2
Launch mobile health units for DR screening | bar: YEAR 2 Q3 to YEAR 3 Q2
Expand effective delivery of DR treatment | bar: YEAR 2 Q2 to YEAR 3 Q2
Medicines and Technology | Advocate for consistent access to essential DR supplies | bar: YEAR 1 Q3 to YEAR 2 Q2
Procure diagnostic equipment for clinics | bar: YEAR 2 Q1 to YEAR 2 Q4
Establish collaborative efforts with tech developers | bar: YEAR 2 Q1 to YEAR 2 Q4
Pilot telemedicine tools for rural DR care | bar: YEAR 2 Q3 to YEAR 3 Q2
Community Engagement | Design and distribute DR education materials | bar: YEAR 1 Q3 to YEAR 2 Q2
Organize community sessions on DR prevention | bar: YEAR 2 Q1 to YEAR 2 Q4
Monitoring and Evaluation | Conduct midterm evaluation | bar: YEAR 2 Q2 to YEAR 2 Q3
Final project evaluation and reporting | bar: YEAR 3 Q2 to YEAR 3 Q3
Publish project outcomes report | bar: YEAR 3 Q4

## Budget
HSS BLOCK | ACTIVITY | YEAR 1 (USD) | YEAR 2 (USD) | YEAR 3 (USD) | TOTAL (USD) |  | YEAR 1 (USD) | YEAR 2 (USD) | YEAR 3 (USD) | TOTAL (USD)
Governance and Leadership | Steering committee formation and meetings | 6000 | 3400 | 3400 | 12800 | ADVOCACY COSTS TOTAL | 91800 | 138550 | 31700 | 262050
| Steering Committee Setup | 200 | 0 | 0 | 200 | SERVICE DELIVERY COSTS TOTAL | 10500 | 291500 | 124400 | 426400
| Monthly Online Meetings | 600 | 0 | 0 | 600 | TECHNOLOGY PILOT | 0 | 30120 | 20080 | 50200
| Quarterly Online Meetings | 200 | 400 | 400 | 1000 | GRAND TOTAL | 102300 | 460170 | 176180 | 738650
| In-Person Meetings | 4000 | 2000 | 2000 | 8000
| Ongoing Meeting Support | 1000 | 1000 | 1000 | 3000
| Development of DR guidelines and policy materials | 6700 | 0 | 0 | 6700
| Stakeholder Engagement Meetings | 900 | 0 | 0 | 900
| Workshops with Policy Influencers | 3000 | 0 | 0 | 3000
| Media and Public Awareness Campaign | 2000 | 0 | 0 | 2000
| Legislative Briefings and Follow-Up | 800 | 0 | 0 | 800
Health Financing | National & provincial funding advocacy | 5600 | 5700 | 700 | 12000
| Initial Research and Proposal Development | 2500 | 0 | 0 | 2500
| Stakeholder Meetings | 600 | 600 | 0 | 1200
| Multi-Stakeholder Roundtables | 1500 | 1500 | 0 | 3000
| Public Advocacy and Media Outreach | 1000 | 1500 | 0 | 2500
| Policy Briefing Sessions | 0 | 1600 | 400 | 2000
| Final Follow-Ups and Documentation | 0 | 500 | 300 | 800
| Partnership development with private sector | 5000 | 2400 | 0 | 7400
| Private Sector Mapping and Outreach Strategy | 1500 | 0 | 0 | 1500
| Initial Meetings with Prospective Partners | 1000 | 0 | 0 | 1000
| Private Sector Engagement Workshop | 2500 | 0 | 0 | 2500
| Formalize Partnerships and Draft Agreements | 0 | 1500 | 0 | 1500
| Kick-Off and Joint Planning Sessions | 0 | 900 | 0 | 900
Health Workforce | Create DR screening and referral training modules | 13500 | 0 | 0 | 13500
| Referral Pathway Mapping and Needs Assessment | 2500 | 0 | 0 | 2500
| Development of Referral Protocols and Guidelines | 3200 | 0 | 0 | 3200
| Curriculum Design and Needs Assessment | 1800 | 0 | 0 | 1800
| Module Content Development | 1700 | 0 | 0 | 1700
| Video and Multimedia Production | 2000 | 0 | 0 | 2000
| Translation and Localization | 1300 | 0 | 0 | 1300
| Pilot Testing and Module Review | 1000 | 0 | 0 | 1000
| Healthcare provider training on DR | 15700 | 46700 | 0 | 62400
| Training Session Planning and Coordination | 5000 | 12200 | 0 | 17200
| Training Materials Production | 2200 | 6500 | 0 | 8700
| Facilitator Fees and Session Delivery | 3000 | 9000 | 0 | 12000
| Participant Stipends and Travel Subsidies | 5500 | 16500 | 0 | 22000
| Monitoring and Evaluation | 0 | 2500 | 0 | 2500
Health Information Systems | Set up DR data collection and reporting systems | 6300 | 15200 | 0 | 21500
| System Design and Requirements Assessment | 2300 | 0 | 0 | 2300
| Software Development and Customization | 4000 | 1500 | 0 | 5500
| Hardware Procurement and Installation | 0 | 7000 | 0 | 7000
| Staff Training and Capacity Building | 0 | 3700 | 0 | 3700
| Pilot Testing and Initial Data Collection | 0 | 1500 | 0 | 1500
| Monitoring, Support, and Final Adjustments | 0 | 1500 | 0 | 1500
| Incorporate DR metrics into national health records | 14800 | 0 | 0 | 14800
| Define DR Metrics and Integration Requirements | 2000 | 0 | 0 | 2000
| System Development and Software Integration | 5000 | 0 | 0 | 5000
| Data Security and Privacy Compliance | 1700 | 0 | 0 | 1700
| Training for Health Information Management Staff | 2900 | 0 | 0 | 2900
| Pilot Testing and Initial Data Collection | 1500 | 0 | 0 | 1500
| Monitoring, Support, and Final Adjustments | 1700 | 0 | 0 | 1700
| Collect data on DR indicators | 0 | 4850 | 4850 | 9700
| Preparation and Coordination | 0 | 850 | 850 | 1700
| Training on Data Collection Procedures | 0 | 750 | 750 | 1500
| Data Collection from Health Facilities | 0 | 1400 | 1400 | 2800
| Data Quality Assurance and Validation | 0 | 750 | 750 | 1500
| Data Analysis and Initial Reporting | 0 | 1100 | 1100 | 2200
Service Delivery | Establish DR screening units at NCD clinics | 6125 | 18375 | 0 | 24500
| Site Assessment and Planning | 1000 | 3000 | 0 | 4000
| Training of Clinic Staff | 2875 | 8625 | 0 | 11500
| Pilot Testing and Quality Assurance | 1125 | 3375 | 0 | 4500
| Ongoing Support and Maintenance Setup | 1125 | 3375 | 0 | 4500
| Establish referral systems | 4375 | 13125 | 0 | 17500
| Implementation of Referral Tracking System | 1125 | 3375 | 0 | 4500
| Training for Healthcare Providers | 1375 | 4125 | 0 | 5500
| Pilot Testing and Quality Assurance | 750 | 2250 | 0 | 3000
| Monitoring and Support for System Rollout | 1125 | 3375 | 0 | 4500
| Perform DR screening in clinics | 0 | 39300 | 26200 | 65500
| Operational Supplies and Consumables | 0 | 7200 | 4800 | 12000
| Community Awareness and Patient Outreach | 0 | 2400 | 1600 | 4000
| Patient Flow and Appointment Coordination | 0 | 1200 | 800 | 2000
| Staffing Support and Screening Personnel Stipends | 0 | 21600 | 14400 | 36000
| Data Collection and Referral Tracking | 0 | 1500 | 1000 | 2500
| Quality Assurance and Compliance Monitoring | 0 | 5400 | 3600 | 9000
| Launch mobile health units for DR screening | 0 | 35000 | 52500 | 87500
| Vehicle Acquisition and Outfitting | 0 | 16000 | 24000 | 40000
| Screening Equipment and Supplies | 0 | 5200 | 7800 | 13000
| Staffing and Training | 0 | 2000 | 3000 | 5000
| Community Outreach and Patient Mobilization | 0 | 1600 | 2400 | 4000
| Operational Costs for Mobile Units | 0 | 8800 | 13200 | 22000
| Data Collection and Quality Assurance | 0 | 1400 | 2100 | 3500
| Expand effective delivery of DR treatment | 0 | 40850 | 40850 | 81700
| Needs Assessment and Treatment Capacity Planning | 0 | 1600 | 1600 | 3200
| Procurement of Treatment Supplies and Equipment | 0 | 19500 | 19500 | 39000
| Specialized Training for Healthcare Providers | 0 | 3500 | 3500 | 7000
| Patient Outreach and Treatment Awareness | 0 | 2500 | 2500 | 5000
| Patient Subsidies and Financial Support | 0 | 10000 | 10000 | 20000
| Monitoring, Evaluation, and Quality Assurance | 0 | 3750 | 3750 | 7500
Medicines and Technology | Advocate for consistent access to essentuial DR supplies | 9400 | 4300 | 0 | 13700
| Stakeholder Engagement and Needs Assessment | 2500 | 0 | 0 | 2500
| Develop Advocacy Materials | 1300 | 0 | 0 | 1300
| Awareness and Media Campaign | 2200 | 0 | 0 | 2200
| Policy Advocacy Meetings and Roundtables | 2400 | 2000 | 0 | 4400
| Supply Chain Engagement and Strategy Development | 1000 | 800 | 0 | 1800
| Monitoring and Evaluation | 0 | 1500 | 0 | 1500
| Procure diagnostic equipment for clinics | 0 | 140000 | 0 | 140000
| Procurement of Screening Equipment | 0 | 120000 | 0 | 120000
| Procurement of Additional Supplies | 0 | 10000 | 0 | 10000
| Delivery and Installation of Equipment | 0 | 10000 | 0 | 10000
| Establish collaborative efforts with tech developers | 0 | 14450 | 0 | 14450
| Identify and Engage Potential Tech Partners | 0 | 1950 | 0 | 1950
| Define Project Goals and Technology Needs | 0 | 2800 | 0 | 2800
| Prototype Development and Demonstration | 0 | 5000 | 0 | 5000
| Legal and Financial Agreement Development | 0 | 2000 | 0 | 2000
| Training and Capacity Building for Tech Integration | 0 | 1500 | 0 | 1500
| Monitoring, Feedback, and Adjustments | 0 | 1200 | 0 | 1200
| Pilot telemedicine tools for rural DR care | 0 | 30120 | 20080 | 50200
| Needs Assessment and Technology Selection | 0 | 1620 | 1080 | 2700
| Procurement of Telemedicine Equipment and Software | 0 | 11700 | 7800 | 19500
| Infrastructure Setup and Connectivity | 0 | 1500 | 1000 | 2500
| Training for Healthcare Providers and Staff | 0 | 4500 | 3000 | 7500
| Pilot Operation and Data Collection | 0 | 8700 | 5800 | 14500
| Monitoring, Evaluation, and Reporting | 0 | 2100 | 1400 | 3500
Community Engagement | Design and distribute DR education materials | 8800 | 5500 | 0 | 14300
| Content Development and Research | 2300 | 0 | 0 | 2300
| Design and Layout of Education Materials | 2500 | 0 | 0 | 2500
| Printing and Production of Materials | 4000 | 0 | 0 | 4000
| Distribution of Educational Materials | 0 | 2300 | 0 | 2300
| Digital Outreach and Social Media Campaign | 0 | 1500 | 0 | 1500
| Evaluation and Feedback Collection | 0 | 1700 | 0 | 1700
| Organize community sessions on DR prevention | 0 | 25900 | 0 | 25900
| Planning and Coordination | 0 | 2800 | 0 | 2800
| Local Partnerships and Community Outreach | 0 | 2700 | 0 | 2700
| Content Preparation and Translation | 0 | 2500 | 0 | 2500
| Community Session Delivery | 0 | 14400 | 0 | 14400
| Post-Session Follow-Up and Support Materials | 0 | 1800 | 0 | 1800
| Monitoring and Evaluation | 0 | 1700 | 0 | 1700
Monitoring and Evaluation | Mid-term evaluation | 0 | 15000 | 0 | 15000
| Evaluation Planning and Framework Development | 0 | 2300 | 0 | 2300
| Data Collection from Project Sites and Stakeholders | 0 | 6200 | 0 | 6200
| Data Analysis and Interpretation | 0 | 3000 | 0 | 3000
| Report Writing and Recommendations | 0 | 2000 | 0 | 2000
| Dissemination of Findings and Follow-Up | 0 | 1500 | 0 | 1500
| Final project evaluation | 0 | 0 | 18100 | 18100
| Evaluation Framework and Planning | 0 | 0 | 2500 | 2500
| Data Collection from Project Sites and Stakeholders | 0 | 0 | 7500 | 7500
| Comprehensive Data Analysis and Interpretation | 0 | 0 | 3700 | 3700
| Final Report Writing and Documentation of Lessons Learned | 0 | 0 | 2700 | 2700
| Dissemination of Findings and Stakeholder Workshop | 0 | 0 | 1700 | 1700
| Publish and disseminate project outcomes report | 0 | 0 | 9500 | 9500
| Final Report Editing and Formatting | 0 | 0 | 2200 | 2200
| Printing and Production of Physical Copies | 0 | 0 | 3000 | 3000
| Digital Publication and Online Distribution | 0 | 0 | 800 | 800
| Dissemination Event or Webinar | 0 | 0 | 2000 | 2000
| Media Outreach and Press Release | 0 | 0 | 1000 | 1000
| Monitoring Report Reach and Impact | 0 | 0 | 500 | 500